## Risk_Register_V1
Risk_ID | Risk description | Impact description | Impact Level (1-5) | Probability Level (1-5) | Priority Level (Impact * probability) | Mitigation Notes | Status | Notes | Date Identified
Risk_01 | Lack of experience | Not all team have computer engineering background which might reduce output efficiency and quality | 5 | 5 | 25 | Prioritize crash courses and training sessions for the team | Open |  | 2026-03-30
Risk_02 | Burnout and time management risk | Team is commited to projects,exams and other courses | 4 | 4 | 16 | Distribute tasks among teams based on previous technical backgrounds to increase productivity and conduct daily meetings to monitor progress | Open |  | 2026-03-30
Risk_03 | Communication issues | Team memebers might face internet connection issues as most of the work and meetings will be done online | 3 | 1 | 3 | Team can utilize coworking spaces for internet connection or ensure all team members have stable internet connection | Open |  | 2026-03-30
Risk_04 | Tools knowledge risks | Not all team members have used tools important for the project such as jira,github and other technical tools | 4 | 3 | 12 | Sharing knowledge among team members and take courses if necessary | Open |  | 2026-03-30
Risk_05 | Tools licence risks | Some important tools might need licence to use which might delay work quality | 2 | 2 | 4 | Use alternative high quality free tools available | Open |  | 2026-03-30
Risk_06 | Members availability | Team memebers might not be available due to sickness or personal issues | 5 | 3 | 15 | Team members should know each other's task progress and ensure work transparency and have alternative plans to compensate for other members being unavailable | Open |  | 2026-03-30
Risk_07 | Client communication risks | Client meets with team members only once a week which affects constant feedback and consultation | 4 | 5 | 20 | Before each sprint, team members should have all questions ready and after the sprint all questions should be answered | Open |  | 2026-03-30
Risk_08 | Client change requests | Client might ask for a change request which might disturb work flow | 5 | 4 | 20 | Team should analyze and priortitize change requests based on importance and should have agreement and rules for change requests | Open |  | 2026-03-30
Risk_09 | Technical debt risks | taking the easy way during SDLC might cause increase in rework cost | 5 | 5 | 25 | Conduct rigorous peer reviews and ensure each step is done efficiently before moving to the next step | Open |  | 2026-03-30
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Date Identified = IF([Risk_ID]<>"", IF([Date Identified]="", TODAY(), [Date Identified]), "")

## SIQs
Module/Feature/Sub-feature | SIQ ID | Question | Proposed answer | Customer answer
Login | SIQ-1 | What are the login feature fields? | Login feature fields are: -Email and Password fields - Login button -Link for user to register if not already registered | Customer agrees
| SIQ-2 | What happens if user leaves fields empty ? | Error message appears under each empty field saying "This field is required" | Customer agrees
| SIQ-3 | What happens when user enters valid credentials? | User is redirected to Explore page | Customer agrees
| SIQ-4 | What happens when user enters invalid credentials with correct email formatting for the email or password fields? | User is prevented from logging in and an error message shows above login button saying "invalid email or password" | Customer agrees
| SIQ-5 | What happens when user enters invalid email format in the email field? | Any invalid email format should be not be allowed (eg. missing @,missing domain,etc..) with error message "invalid email format" | Customer agrees
| SIQ-6 | What happens when user clicks on Create account button? | User is redirected to Registration page | Customer agrees
| SIQ-7 | What happens when admin logs in successfully? | Admin is redirected to User management page | Customer agrees
| SIQ-8 | Should admin have a separate login page or the same one as the user ? | The same one as the user. | Customer agrees
| SIQ-9 | Is there a rate limit for amount of login attempts ? | Yes, user is locked out after 5 wrong attempts with message appearing above login button "Please try again in 60 seconds" and countdown until message disappears. In the lock out period login button is disabled. | Customer agrees
Register | SIQ-10 | What are the register feature fields? | Register feature fields are : -First name -Last name -Email -Password -Confirm password -Register button -Link to redirect user if already having an account to login | Customer agrees
| SIQ-11 | What happens if user leaves any field empty? | Error message appears under each empty field saying "This field is required" | Customer agrees
| SIQ-12 | Is there a minimum or maximum number of characters for any field? | -name fields : max 50 char , min 2 char, error message: " First name/Last name must be between 2 to 50 characters" -password field: min 8 characters ,error message: "password should be at least 8 characters long" | Customer agrees
| SIQ-13 | Are there any password complexity requirements ? | Yes at least one small letter, one capital letter, one number and one special character | Customer agrees
| SIQ-14 | What happens when user enters password that doesn't meet complexity | Message appears under password field saying "password should have one small letter,one capital letter,one number and one special character" | Customer agrees
| SIQ-15 | What happens when user enters password with length below minimum? | Error message appears under pasword field "Password must be at least 8 characters long" | Customer agrees
| SIQ-16 | What happens when user enters password that doesn't match password in confirm password field? | Error message shows under confirm password field "Password doesn't match" | Customer agrees
| SIQ-17 | What happens when user enters invalid email format in the email field? | Any invalid email format should be not be allowed (eg. missing @,missing domain,etc..) | Customer agrees
| SIQ-18 | Can name fields contain numbers or special characters? | Only alphabetic characters allowed | Customer agrees
| SIQ-19 | Should user be redirected to Explore page or login page after successful registration? | Explore page | Customer agrees
| SIQ-20 | What happens if a user enters an email that is already registered ? | An error message shows above Register button "Email already has an account" | Customer agrees
| SIQ-21 | What happens when user clicks on Login link? | User is redirected to login page | Customer agrees
Explore/Home | SIQ-22 | What are the main features in Explore page other than gallery of top travel destinations? | The home screen contains the following features: -Navigation bar with these nav links/buttons : Explore, Find flights,My bookings , Logout button and current page should be underlined -A section where user can choose from touristic countries -At max 9 images for each country which update dynamically based on user country choice -"View tour" button to navigate to page with details for each page -customer reviews section for the website at the bottom | Customer agrees
| SIQ-23 | Where should user be redirected after clicking on Logout button? | User should be redirected to login page | Customer agrees
Destination Details | SIQ-24 | What are the components/features of this page? | -A banner/image for the destination as shown in explore page -Text that describes the place -Labeled pictures to show remarkable views of the destination | Customer agrees
| SIQ-25 | - what happens when the user clicks on the Booking button? | - Booking button to take user to Find flights page to start the booking flow after viewing the destination | Customer agrees
Flight Search Page / Find Flights | SIQ-26 | Does the page include only the required fields (Departure, Destination, Dates) without extra elements? | The page contains exactly three input fields and a Search button as specified | Customer shows no objections.
| SIQ-27 | Does the system validate that all fields (Departure, Destination, Dates) are filled before searching? | The system prevents search and displays an error message under field if any field is empty | Customer shows no objections.
| SIQ-28 | Can the user select the same city for Departure and Destination? | The system prevents selecting the same location and shows a warning message | Customer shows no objections.
| SIQ-29 | Does clicking the Search button display flight results on the same page? | Results are displayed dynamically on the same page without redirection | Customer shows no objections.
| SIQ-30 | Does the "Select Flight" button navigate the user to the payment page? | Upon selecting a flight, the user is redirected to the payment page | Customer shows no objections.
| SIQ-31 | What happens if no flights are found? | The system displays a "No search results" message | Customer shows no objections.
Passenger Details | SIQ-32 | What fields should be present? | Full name, passport number, and date of birth | Customer shows no objections.
| SIQ-33 | What validations are required? | Each field is mandatory and cannot be left empty | Customer shows no objections.
| SIQ-34 | What happens if a required field is empty? | A validation error message is displayed under the corresponding field | Customer shows no objections.
| SIQ-35 | What validation is applied to Full Name field? | Accepts alphabetic characters only (A–Z) | Customer shows no objections.
| SIQ-36 | What are the length constraints for Full Name? | Minimum 3 characters and maximum 30 characters | Customer shows no objections.
| SIQ-37 | What validation is applied to passport number? | Accepts alphanumeric characters only | Customer shows no objections.
| SIQ-38 | Are spaces allowed in passport number? | No, spaces are not allowed | Customer shows no objections.
| SIQ-39 | Can the user enter a future date of birth? | No, date of birth must be in the past | Customer shows no objections.
Payment | SIQ-40 | What fields should be present? | Card number, cardholder name, expiry date, CVV, and "Pay & Confirm Booking" button | Customer shows no objections.
| SIQ-41 | What validations are required? | All fields must not be empty | Customer shows no objections.
| SIQ-42 | What happens when user clicks on "Pay & Confirm Booking" button | user is redirect to “Share Your Experience” page with popup message | Customer shows no objections.
| SIQ-43 | What happens when user clicks cancel button on Share Experience page? | User is redirected to My Bookings page | Customer shows no objections.
| SIQ-44 | What happens when user clicks Submit button on Share Experience page? | User is redirected to My Bookings page | Customer shows no objections.
My Bookings | SIQ-45 | What are the contents of My Bookings page? | Page should contain: -Full user name and Unique ID at the top of the page -Past bookings section that shows previously booked destinations -Book again button for each destination | Customer shows no objections.
| SIQ-46 | What happens when user clicks on Book again button? | The user should be redirected to the Find Flights page, with the Destination field pre-filled with the selected destination for rebooking. | Customer shows no objections.
| SIQ-47 | What should show if user has not made any bookings yet in past bookings section | No bookings to show | Customer shows no objections.
User Management (Admin Feature) | SIQ-48 | What are the admin authorities in User Management page? | Admin shall be able to view all registered users | Customer shows no objections.
| SIQ-49 | What operations can the admin perform on users? | Admin shall be able to delete users | Customer shows no objections.
| SIQ-50 | How can the admin navigate through users? | The system shall allow admin to browse users using pagination. | Customer shows no objections.
| SIQ-51 | What happens when admin tries to delete a user? | The system shall display a confirmation prompt before deleting the user, allowing the admin to either confirm or cancel the action. | Customer shows no objections.
Booking Histoy (Admin Feature) | SIQ-52 | What are the authorities of an admin in Booking History page? | Admin should be able to view all booked flights made by users. | Customer shows no objections.
| SIQ-53 | How can the admin navigate through bookings? | The system shall allow the admin to browse all bookings using pagination. | Customer shows no objections.
| SIQ-54 | What action can the admin perform on a booking? | Admin should be able to cancel a booked flight. | Customer shows no objections.
| SIQ-55 | What happens when admin tries to cancel a booking? | The system shall display a confirmation prompt before canceling the booking. | Customer shows no objections.
| SIQ-56 | What happens if admin confirms cancellation? | The system shall cancel the booking. | Customer shows no objections.
| SIQ-57 | What happens if admin cancels the action? | The system shall keep the booking unchanged. | Customer shows no objections.

## Test Cases
TesTCASE ID | Test Cases Title | valid/invaldid | Environment | Pre-condition | Steps | Test Data | Expected Results | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Comment
TC_Registration_001 | Verify registration feature in case of user registering with valid data for all fields | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-09 | Functional | Ahmed Zahran
TC_Registration_002 | Verify registration feature in case of user clicking on login link | valid |  | User is already on registration page | 1-Navigate to login link 2- Click on login link |  | User should successfully be redirected to Login page |  | Draft |  | UR-10 | Functional | Ahmed Zahran
TC_Registration_003 | Verify registration feature in case of user entering First name that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_004 | Verify registration feature in case of user entering First name that is exactly the maximim allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_005 | Verify registration feature in case of user entering Last name that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_006 | Verify registration feature in case of user entering Last name that is exactly the maxiimum allowed character length | valid |  | User is already on registration page | "1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button" |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_007 | Verfiy registration feature in case of user entering password that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_008 | Verify registration feature in case of user entering first name that is less than minimum allowed character length | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_009 | Verify registration feature in case of user entering first name that is more than maximum allowed character length | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_010 | Verify registration feature in case of user entering Last name that is less than the minimum allowed character length | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_011 | Verify registration feature in case of user entering Last name that is more than the maximum allowed character length | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_012 | Verify registration feature in case of user entering a password that is less than minmum allowed character length | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear below password field "password cannot be less than 8 characters" |  | Draft |  | UR-03 | Functional | Ahmed Zahran
TC_Registration_013 | Verify registration feature in case of user entering password that is missing a small letter | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_014 | Verify registration feature in case of user entering password that is missing a capital letter | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_015 | Verify registration feature in case of user entering password that is missing a number | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_016 | Verify registration feature in case of user entering password that is missing a special character | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_017 | Verify registration feature in case of user entering password in confirm password field that doesn't match password in pasword field | Invalid |  | User is already on registration page | 1-Enter password in password field 2-Enter confirmation password in confirm password field |  | Error message should appear under confirm password field "password doesn't match" |  | Draft |  | UR-05 | Functional | Ahmed Zahran
TC_Registration_018 | Verify registration feature in case of user entering an invalid email format that is missing '@' in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_019 | Verify registration feature in case of user entering an invalid email format that is missing username in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_020 | Verify registration feature in case of user entering an invalid email format that is missing domain in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_021 | Verify regirstation feature in case of user entering First name that contains special characters | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear under First name field "Only alphabetic characters are allowed" |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_022 | Verify regirstation feature in case of user entering First name that contains numbers | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear under First name field "Only alphabetic characters are allowed" |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_023 | Verify regirstation feature in case of user entering Last name that contains special characters | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear under Last name field "Only alphabetic characters are allowed" |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_024 | Verify regirstation feature in case of user entering Last name that contains numbers | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear under Last name field "Only alphabetic characters are allowed" |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_025 | Verify registration feature in case of user registering with an email that is already registered | Invalid |  | 1-User is already registered 2-User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | Error message appears above Create account button "Email already has an account" |  | Draft |  | UR-08 | Functional | Ahmed Zahran
TC_Registration_026 | Verify registration feature in case of user registering with empty First name field | Invalid |  | User is already on registration page | 1-Enter last name in Last name field 2-Enter email in Email field 3-Enter password in password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below First name field " This field is required" |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_027 | Verify registration feature in case of user registering with empty Last name field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter email in Email field 3-Enter password in password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Last name field " This field is required" |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_028 | Verify registration feature in case of user registering with empty password field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Password field " This field is required" |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_029 | Verify registration feature in case of user registering with empty email field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter password in Password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Email field " This field is required" |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_030 | Verify registration feature in case of user registering with empty Confirm password field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last field 3-Enter email in Email field 4-Enter password in Password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Confirm password field " This field is required" |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_HomePage_01 | The system shall redirect the user to the “Find Flights” Page when the user clicks on “Find Flights” in the navigation bar. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Find Flights" Button in the navigation bar | N/A | 1- The user is redirected to the "Find Flights" Page to search for a flight |  | Draft |  |  | Functional | Alaa
TC_HomePage_02 | The system shall redirect the user to the “My Bookings” Page when the user clicks on “My Bookings” in the navigation bar to show previous bookings. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "My Bookings" Button in the navigation bar | N/A | 1- The user is redirected to the "My Bookings" Page to show previous bookings |  | Draft |  |  | Functional | Alaa
TC_HomePage_03 | The system shall stay on the same page when the user clicks on “Explore” in the navigation bar. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Explore" Button in the navigation bar | N/A | 1- The user stays on the same page |  | Draft |  |  | Functional | Alaa
TC_HomePage_04 | The system shall redirect the user to the “Login” Page when the user clicks on “LOGOUT” in the navigation bar to login again. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Login" Button in the navigation bar | N/A | 1- The user is redirected to the "login" Page and asked to login again |  | Draft |  |  | Functional | Alaa
TC_HomePage_05 | The system shall show 9 tour cards of Italy when clicking “Italy”, showing tour rating, cost, and “View Tour” button to show tour details. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "Italy" button | N/A | 1- The system shows 9 tour cards of top destinations in Italy |  | Draft |  |  | Functional | Alaa | Feels Like UI
TC_HomePage_06 | The system shall show 9 tour cards of France when clicking “France”, showing tour rating, cost, and “View Tour” button to show tour details. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "France" button | N/A | 1- The system shows 9 tour cards of top destinations in France |  | Draft |  |  | Functional | Alaa | Feels Like UI
TC_HomePage_07 | The system shall show 9 tour cards of Egypt when clicking “Egypt”, showing tour rating, cost, and “View Tour” button to show tour details. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "Egypt" button | N/A | 1- The system shows 9 tour cards of top destinations in Egypt |  | Draft |  |  | Functional | Alaa | Feels Like UI
TC_HomePage_08 | The system shall redirect the user to the corresponding Destination Details Page when the user clicks on “View Tour” in any tour card. | valid | Web App | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on "View Tour" Button in any tour card. | N/A | 1- The user is redirected to the corresponding Destination Details Page |  | Draft |  |  | Functional | Alaa
TC_DestinationDetails_01 | The system shall allow the user to proceed to the booking flow by clicking the “Book Flight” button. | valid | Web App | The User is logged in and is on the Home(Explore) Page and is on the destination details page after clicking "view tour" on any card | 1- The User Clicks "Book Flight". | N/A | 1- The user is redirected to the "Find Flights" Page with the Destination Field set to the re-booked destination |  | Draft |  |  | Functional | Alaa
TC-PassangerDetails-01 | Verify submission of valid passenger details | valid | Web App | User on Passenger Details page | Enter all valid data | Ahmed Ali / A1234567 / 10-10-2000 | Data accepted and stored temporarily | Data saved |  |  | PD-01,PD-06 | Functional | Abdelrahman khaled
TC-PassangerDetails-02 | Validate required Full Name field when left empty | Invalid | Web App | User on Passenger Details page | Leave Full Name empty | "" / A1234567 / 10-10-2000 | Error “This field is required” under Full Name | No data saved |  |  | PD-02,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-03 | Validate required Passport Number field when left empty | Invalid | Web App | User on Passenger Details page | Leave Passport empty | Ahmed Ali / "" / 10-10-2000 | Error message displayed under Passport | No data saved |  |  | PD-03,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-04 | Validate required Date of Birth field when left empty | Invalid | Web App | User on Passenger Details page | Leave DOB empty | Ahmed Ali / A1234567 / "" | Error message displayed under DOB | No data saved |  |  | PD-04,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-05 | Validate Full Name rejects numeric characters | Invalid | Web App | User on Passenger Details page | Enter invalid name | Ahmed123 | Error message displayed | No data saved |  |  | PD-07,PD-08 | Functional | Abdelrahman khaled
TC-PassangerDetails-06 | Validate Full Name rejects special characters | Invalid | Web App | User on Passenger Details page | Enter invalid name | Ahmed@Ali | Error message displayed | No data saved |  |  | PD-07,PD-08 | Functional | Abdelrahman khaled
TC-PassangerDetails-07 | Validate Full Name minimum length constraint (less than 3 characters) | Invalid | Web App | User on Passenger Details page | Enter short name | Ah | Error message displayed | No data saved |  |  | PD-09 | Functional | Abdelrahman khaled
TC-PassangerDetails-08 | Validate Full Name maximum length constraint (more than 30 characters) | Invalid | Web App | User on Passenger Details page | Enter long name | 31+ chararacters | Error message displayed | No data saved |  |  | PD-09 | Functional | Abdelrahman khaled
TC-PassangerDetails-09 | Validate Passport Number rejects special characters | Invalid | Web App | User on Passenger Details page | Enter invalid passport | A12@456 | Error message displayed | No data saved |  |  | PD-10 | Functional | Abdelrahman khaled
TC-PassangerDetails-10 | Validate Passport Number rejects spaces | Invalid | Web App | User on Passenger Details page | Enter passport with space | A12 3456 | Error message displayed | No data saved |  |  | PD-11 | Functional | Abdelrahman khaled
TC-PassangerDetails-11 | Validate Date of Birth does not accept future dates | Invalid | Web App | User on Passenger Details page | Enter future DOB | 2050-01-01 | Error message displayed | No data saved |  |  | PD-12 | Functional | Abdelrahman khaled
TC-Payment-01 | Verify successful payment with valid card details | valid | Web App | User on Payment page | 1-Enter valid data in all fields 2-Click Pay & Confirm | 4111111111111111 / Ahmed Ali / 12/26 / 123 | Payment processed successfully | Redirect to Share Experience page with popup |  |  | PAY-01 | Functional | Abdelrahman khaled
TC-Payment-02 | Validate empty Card Number field on payment submission | Invalid | Web App | User on Payment page | 1-Leave Card Number empty 2-Click Pay & Confirm | ""/ Ahmed Ali / 12/26 / 123 | Error “This field is required” shown | No payment |  |  | PAY-02,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-03 | Validate empty Cardholder Name field on payment submission | Invalid | Web App | User on Payment page | 1-Leave Name empty 2-Click Pay & Confirm | Empty Name | Error “This field is required” shown | No payment |  |  | PAY-03,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-04 | Validate empty Expiry Date field on payment submission | Invalid | Web App | User on Payment page | 1-Leave Expiry empty 2-Click Pay & Confirm | Empty Expiry | Error “This field is required” shown | No payment |  |  | PAY-04,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-05 | Validate empty CVV field on payment submission | Invalid | Web App | User on Payment page | 1-Leave CVV empty 2-Click Pay & Confirm | Empty CVV | Error “This field is required” shown | No payment |  |  | PAY-05,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-06 | Verify payment processing is triggered on Pay & Confirm button click | valid | Web App | All fields filled | Click Pay & Confirm | Valid data | Payment process starts | Redirect to Share Experience page |  |  | PAY-06 | Functional | Abdelrahman khaled
TC-Payment-07 | Verify redirection to Share Experience page after successful payment | valid | Web App | Payment successful | Complete payment | Valid payment | User redirected to Share Experience page | Page navigation completed |  |  | PAY-08 | Functional | Abdelrahman khaled
TC-Payment-08 | Verify redirection to My Bookings page on clicking Cancel button | valid | Web App | User on Share Experience page | Click Cancel | N/A | User redirected to My Bookings page | Navigation success |  |  | PAY-09 | Functional | Abdelrahman khaled
TC-Payment-09 | Verify redirection to My Bookings page on clicking Submit button | valid | Web App | User on Share Experience page | Click Submit | N/A | User redirected to My Bookings page | Navigation success |  |  | PAY-10 | Functional | Abdelrahman khaled
TC-UserManagement-01 | Verify admin can view all registered users | valid | Web App | Admin logged in | Open User Management page | N/A | List of all users displayed | Users visible |  |  | UM-01,UM-02 | Functional | Abdelrahman khaled
TC-UserManagement-02 | Verify pagination allows admin to browse users | valid | Web App | Users exist in multiple pages | Navigate next/previous page | N/A | Users change per page correctly | Page updated |  |  | UM-03 | Functional | Abdelrahman khaled
TC-UserManagement-03 | Verify delete action triggers confirmation prompt | valid | Web App | Admin on User Management page | Click delete on user | User ID: 101 | Confirmation popup displayed | No deletion yet |  |  | UM-05 | Functional | Abdelrahman khaled
TC-UserManagement-04 | Verify user is deleted when admin confirms deletion | valid | Web App | Confirmation prompt displayed | Click Confirm | User ID: 101 | User is removed from system | User deleted |  |  | UM-04,UM-06,UM-08 | Functional | Abdelrahman khaled
TC-UserManagement-05 | Verify user is not deleted when admin cancels deletion | valid | Web App | Confirmation prompt displayed | Click Cancel | User ID: 101 | User remains in system | No change |  |  | UM-07 | Functional | Abdelrahman khaled
TC-BookingHistory-01 | Verify admin can view all booked flights | valid | Web App | Admin logged in | Open Booking History page | N/A | All user bookings displayed | Bookings visible |  |  | BH-01,BH-02 | Functional | Abdelrahman khaled
TC-BookingHistory-02 | Verify pagination allows browsing through bookings | valid | Web App | Multiple bookings exist | Navigate next/previous pages | N/A | Booking list updates per page | Page updated |  |  | BH-03 | Functional | Abdelrahman khaled
TC-BookingHistory-03 | Verify confirmation prompt appears when canceling booking | valid | Web App | Admin on Booking History page | Click cancel booking | Booking ID: 101 | Confirmation popup displayed | No change yet |  |  | BH-05 | Functional | Abdelrahman khaled
TC-BookingHistory-04 | Verify booking is canceled when admin confirms action | valid | Web App | Confirmation popup shown | Click Confirm | Booking ID: 101 | Booking is removed/canceled | Booking deleted |  |  | BH-04,BH-06,BH-08 | Functional | Abdelrahman khaled
TC-BookingHistory-05 | Verify booking remains unchanged when admin cancels action | valid | Web App | Confirmation popup shown | Click Cancel | Booking ID: 101 | Booking remains unchanged | No update |  |  | BH-07 | Functional | Abdelrahman khaled
TC-FlightSearch-01 | Valid that Flight Search results appears after entering valid search info. | valid |  |  |  |  | system should redirect the users to the personal details and the payment page if the “Select Journey” button has been pressed |  | Draft |  | FSR-01 | Functional | Al-Hussein
TC-FlightSearch-02 | Valid that Flight Search results appears after entering invalid search info. | Invalid |  |  |  |  | System should give no results |  | Draft |  | FSR-01 | Functional | Al-Hussein
TC_Login_001 | Verify login feature in case of user entering valid email and password | valid |  | 1-User should be already registered 2-User is already on login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | User shoould gain access and should be redirected to homepage |  | Draft |  | UL-06 | Functional | Ahmed Zahran
TC_Login_002 | Verify login feature in case of admin entering valid email and password | valid |  | Admin should be already on login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | Admin should gain access and should be redirected to User management page |  | Draft |  | UL-05 | Functional
TC_Login_003 | Verify login feature in case of user clicking on Create account button | valid |  | User is already on login page | 1-Navigate to Create account link 2-Click on the Create account link |  | User should be redirected to sign up page to register as a new user |  | Draft |  | UL-04 | Functional | Ahmed Zahran
TC_Login_004 | Verify login feature in case of user clicking on Login button when email field is empty | Invalid |  | User is already on login page | 1-Enter password in password field 2-Click on Login button |  | User should be prevented from log in and error message appears under email field "This field is required" |  | Draft |  | UL-01 | Functional | Ahmed Zahran
TC_Login_005 | Verify login feature in case of user clicking on Login button when password field is empty | Invalid |  | User is already on login page | 1-Enter email address in email field 2-Click on Login button |  | User should be prevented from log in and error message appears under password field "This field is required" |  | Draft |  | UL-01 | Functional | Ahmed Zahran
TC_Login_006 | Verify login feature in case of user logging in using invalid email format which is missing '@' | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_007 | Verify login feature in case of user logging in using invalid email format which is missing username | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_008 | Verify login feature in case of user logging in using invalid email format which is missing domain | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_009 | Verify login feature in case of user logging with invalid credentials | Invalid |  | User is already on Login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | Error message should appear above login button "Invalid email or password" |  | Draft |  | UL-03 | Functional | Ahmed Zahran
TC-MyBookings_01 | Verify my bookings feature in case of user clicking on Book Again button | valid |  | User is already on My Bookings page | 1-Navigate to any previous booking in past bookings section 2-Click on Book Again button |  | User should be redirected to Find Flights page and Destination field should be prefilled with selected destination |  | Draft |  | MB-01 | Functional | Ahmed Zahran

## Test Execution
TesTCASE ID | execution status | Test Cases Title | valid/invaldid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual result | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Comment
TC_Registration_001 |  | Verify registration feature in case of user registering with valid data for all fields | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-09 | Functional | Ahmed Zahran
TC_Registration_002 |  | Verify registration feature in case of user clicking on login link | valid |  | User is already on registration page | 1-Navigate to login link 2- Click on login link |  | User should successfully be redirected to Login page |  |  | Draft |  | UR-10 | Functional | Ahmed Zahran
TC_Registration_003 |  | Verify registration feature in case of user entering First name that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_004 |  | Verify registration feature in case of user entering First name that is exactly the maximim allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_005 |  | Verify registration feature in case of user entering Last name that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_006 |  | Verify registration feature in case of user entering Last name that is exactly the maxiimum allowed character length | valid |  | User is already on registration page | "1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button" |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_007 |  | Verfiy registration feature in case of user entering password that is exactly the minimum allowed character length | valid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | User should successfully be redirected to Explore/home page |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_008 |  | Verify registration feature in case of user entering first name that is less than minimum allowed character length | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_009 |  | Verify registration feature in case of user entering first name that is more than maximum allowed character length | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_010 |  | Verify registration feature in case of user entering Last name that is less than the minimum allowed character length | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_011 |  | Verify registration feature in case of user entering Last name that is more than the maximum allowed character length | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear below First name field "Name should be between 2 and 50 characters |  |  | Draft |  | UR-02 | Functional | Ahmed Zahran
TC_Registration_012 |  | Verify registration feature in case of user entering a password that is less than minmum allowed character length | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear below password field "password cannot be less than 8 characters" |  |  | Draft |  | UR-03 | Functional | Ahmed Zahran
TC_Registration_013 |  | Verify registration feature in case of user entering password that is missing a small letter | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_014 |  | Verify registration feature in case of user entering password that is missing a capital letter | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_015 |  | Verify registration feature in case of user entering password that is missing a number | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_016 |  | Verify registration feature in case of user entering password that is missing a special character | Invalid |  | User is already on registration page | Enter password in Password field |  | Error message should appear under password field “password should have one small letter,one capital letter,one number and one special character” |  |  | Draft |  | UR-04 | Functional | Ahmed Zahran
TC_Registration_017 |  | Verify registration feature in case of user entering password in confirm password field that doesn't match password in pasword field | Invalid |  | User is already on registration page | 1-Enter password in password field 2-Enter confirmation password in confirm password field |  | Error message should appear under confirm password field "password doesn't match" |  |  | Draft |  | UR-05 | Functional | Ahmed Zahran
TC_Registration_018 |  | Verify registration feature in case of user entering an invalid email format that is missing '@' in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_019 |  | Verify registration feature in case of user entering an invalid email format that is missing username in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_020 |  | Verify registration feature in case of user entering an invalid email format that is missing domain in email field | Invalid |  | User is already on registration page | Enter email in Email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UR-06 | Functional | Ahmed Zahran
TC_Registration_021 |  | Verify regirstation feature in case of user entering First name that contains special characters | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear under First name field "Only alphabetic characters are allowed" |  |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_022 |  | Verify regirstation feature in case of user entering First name that contains numbers | Invalid |  | User is already on registration page | Enter first name in First name field |  | Error message should appear under First name field "Only alphabetic characters are allowed" |  |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_023 |  | Verify regirstation feature in case of user entering Last name that contains special characters | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear under Last name field "Only alphabetic characters are allowed" |  |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_024 |  | Verify regirstation feature in case of user entering Last name that contains numbers | Invalid |  | User is already on registration page | Enter last name in Last name field |  | Error message should appear under Last name field "Only alphabetic characters are allowed" |  |  | Draft |  | UR-07 | Functional | Ahmed Zahran
TC_Registration_025 |  | Verify registration feature in case of user registering with an email that is already registered | Invalid |  | 1-User is already registered 2-User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter password in password field 5-Enter confirm password in Confirm password field 6-Click on Create account button |  | Error message appears above Create account button "Email already has an account" |  |  | Draft |  | UR-08 | Functional | Ahmed Zahran
TC_Registration_026 |  | Verify registration feature in case of user registering with empty First name field | Invalid |  | User is already on registration page | 1-Enter last name in Last name field 2-Enter email in Email field 3-Enter password in password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below First name field " This field is required" |  |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_027 |  | Verify registration feature in case of user registering with empty Last name field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter email in Email field 3-Enter password in password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Last name field " This field is required" |  |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_028 |  | Verify registration feature in case of user registering with empty password field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter email in Email field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Password field " This field is required" |  |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_029 |  | Verify registration feature in case of user registering with empty email field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last name field 3-Enter password in Password field 4-Enter confirm password in Confirm password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Email field " This field is required" |  |  | Draft |  | UR-01 | Functional | Ahmed Zahran
TC_Registration_030 |  | Verify registration feature in case of user registering with empty Confirm password field | Invalid |  | User is already on registration page | 1-Enter first name in First name field 2-Enter last name in Last field 3-Enter email in Email field 4-Enter password in Password field 5-Click on Create account button |  | User should be prevented from registration and error message appears below Confirm password field " This field is required" |  |  | Draft |  | UR-01 | Functional | Ahmed Zahran
Draft
TC_HomePage_01 |  | The system shall redirect the user to the “Find Flights” Page when the user clicks on “Find Flights” in the navigation bar. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Find Flights" Button in the navigation bar |  | 1- The user is redirected to the "Find Flights" Page to search for a flight |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_02 |  | The system shall redirect the user to the “My Bookings” Page when the user clicks on “My Bookings” in the navigation bar to show previous bookings. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "My Bookings" Button in the navigation bar |  | 1- The user is redirected to the "My Bookings" Page to show previous bookings |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_03 |  | The system shall stay on the same page when the user clicks on “Explore” in the navigation bar. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Explore" Button in the navigation bar |  | 1- The user stays on the same page |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_04 |  | The system shall redirect the user to the “Login” Page when the user clicks on “LOGOUT” in the navigation bar to login again. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on the "Login" Button in the navigation bar |  | 1- The user is redirected to the "login" Page and asked to login again |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_05 |  | The system shall show 9 tour cards of Italy when clicking “Italy”, showing tour rating, cost, and “View Tour” button to show tour details. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "Italy" button |  | 1- The system shows 9 tour cards of top destinations in Italy |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_06 |  | The system shall show 9 tour cards of France when clicking “France”, showing tour rating, cost, and “View Tour” button to show tour details. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "France" button |  | 1- The system shows 9 tour cards of top destinations in France |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_07 |  | The system shall show 9 tour cards of Egypt when clicking “Egypt”, showing tour rating, cost, and “View Tour” button to show tour details. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The user clicks on "Egypt" button |  | 1- The system shows 9 tour cards of top destinations in Egypt |  |  | Draft |  |  | Functional | Alaa
TC_HomePage_08 |  | The system shall redirect the user to the corresponding Destination Details Page when the user clicks on “View Tour” in any tour card. | valid |  | The User is logged in and is on the Home(Explore) Page | 1- The User Clicks on "View Tour" Button in any tour card. |  | 1- The user is redirected to the corresponding Destination Details Page |  |  | Draft |  |  | Functional | Alaa
Draft
TC_DestinationDetails_01 |  | The system shall allow the user to proceed to the booking flow by clicking the “Book Flight” button. | valid |  | The User is logged in and is on the Home(Explore) Page and is on the destination details page after clicking "view tour" on any card | 1- The User Clicks "Book Flight". |  | 1- The user is redirected to the "Find Flights" Page with the Destination Field set to the re-booked destination |  |  | Draft |  |  | Functional | Alaa
Draft
TC-PassangerDetails-01 |  | Verify submission of valid passenger details | valid |  | User on Passenger Details page | Enter all valid data |  | Data accepted and stored temporarily |  |  | Draft |  | PD-01,PD-06 | Functional | Abdelrahman khaled
TC-PassangerDetails-02 |  | Validate required Full Name field when left empty | Invalid |  | User on Passenger Details page | Leave Full Name empty |  | Error “This field is required” under Full Name |  |  | Draft |  | PD-02,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-03 |  | Validate required Passport Number field when left empty | Invalid |  | User on Passenger Details page | Leave Passport empty |  | Error message displayed under Passport |  |  | Draft |  | PD-03,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-04 |  | Validate required Date of Birth field when left empty | Invalid |  | User on Passenger Details page | Leave DOB empty |  | Error message displayed under DOB |  |  | Draft |  | PD-04,PD-05 | Functional | Abdelrahman khaled
TC-PassangerDetails-05 |  | Validate Full Name rejects numeric characters | Invalid |  | User on Passenger Details page | Enter invalid name |  | Error message displayed |  |  | Draft |  | PD-07,PD-08 | Functional | Abdelrahman khaled
TC-PassangerDetails-06 |  | Validate Full Name rejects special characters | Invalid |  | User on Passenger Details page | Enter invalid name |  | Error message displayed |  |  | Draft |  | PD-07,PD-08 | Functional | Abdelrahman khaled
TC-PassangerDetails-07 |  | Validate Full Name minimum length constraint (less than 3 characters) | Invalid |  | User on Passenger Details page | Enter short name |  | Error message displayed |  |  | Draft |  | PD-09 | Functional | Abdelrahman khaled
TC-PassangerDetails-08 |  | Validate Full Name maximum length constraint (more than 30 characters) | Invalid |  | User on Passenger Details page | Enter long name |  | Error message displayed |  |  | Draft |  | PD-09 | Functional | Abdelrahman khaled
TC-PassangerDetails-09 |  | Validate Passport Number rejects special characters | Invalid |  | User on Passenger Details page | Enter invalid passport |  | Error message displayed |  |  | Draft |  | PD-10 | Functional | Abdelrahman khaled
TC-PassangerDetails-10 |  | Validate Passport Number rejects spaces | Invalid |  | User on Passenger Details page | Enter passport with space |  | Error message displayed |  |  | Draft |  | PD-11 | Functional | Abdelrahman khaled
TC-PassangerDetails-11 |  | Validate Date of Birth does not accept future dates | Invalid |  | User on Passenger Details page | Enter future DOB |  | Error message displayed |  |  | Draft |  | PD-12 | Functional | Abdelrahman khaled
Draft
TC-Payment-01 |  | Verify successful payment with valid card details | valid |  | User on Payment page | 1-Enter valid data in all fields 2-Click Pay & Confirm |  | Payment processed successfully |  |  | Draft |  | PAY-01 | Functional | Abdelrahman khaled
TC-Payment-02 |  | Validate empty Card Number field on payment submission | Invalid |  | User on Payment page | 1-Leave Card Number empty 2-Click Pay & Confirm |  | Error “This field is required” shown |  |  | Draft |  | PAY-02,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-03 |  | Validate empty Cardholder Name field on payment submission | Invalid |  | User on Payment page | 1-Leave Name empty 2-Click Pay & Confirm |  | Error “This field is required” shown |  |  | Draft |  | PAY-03,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-04 |  | Validate empty Expiry Date field on payment submission | Invalid |  | User on Payment page | 1-Leave Expiry empty 2-Click Pay & Confirm |  | Error “This field is required” shown |  |  | Draft |  | PAY-04,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-05 |  | Validate empty CVV field on payment submission | Invalid |  | User on Payment page | 1-Leave CVV empty 2-Click Pay & Confirm |  | Error “This field is required” shown |  |  | Draft |  | PAY-05,PAY-07 | Functional | Abdelrahman khaled
TC-Payment-06 |  | Verify payment processing is triggered on Pay & Confirm button click | valid |  | All fields filled | Click Pay & Confirm |  | Payment process starts |  |  | Draft |  | PAY-06 | Functional | Abdelrahman khaled
TC-Payment-07 |  | Verify redirection to Share Experience page after successful payment | valid |  | Payment successful | Complete payment |  | User redirected to Share Experience page |  |  | Draft |  | PAY-08 | Functional | Abdelrahman khaled
TC-Payment-08 |  | Verify redirection to My Bookings page on clicking Cancel button | valid |  | User on Share Experience page | Click Cancel |  | User redirected to My Bookings page |  |  | Draft |  | PAY-09 | Functional | Abdelrahman khaled
TC-Payment-09 |  | Verify redirection to My Bookings page on clicking Submit button | valid |  | User on Share Experience page | Click Submit |  | User redirected to My Bookings page |  |  | Draft |  | PAY-10 | Functional | Abdelrahman khaled
Draft
TC-UserManagement-01 |  | Verify admin can view all registered users | valid |  | Admin logged in | Open User Management page |  | List of all users displayed |  |  | Draft |  | UM-01,UM-02 | Functional | Abdelrahman khaled
TC-UserManagement-02 |  | Verify pagination allows admin to browse users | valid |  | Users exist in multiple pages | Navigate next/previous page |  | Users change per page correctly |  |  | Draft |  | UM-03 | Functional | Abdelrahman khaled
TC-UserManagement-03 |  | Verify delete action triggers confirmation prompt | valid |  | Admin on User Management page | Click delete on user |  | Confirmation popup displayed |  |  | Draft |  | UM-05 | Functional | Abdelrahman khaled
TC-UserManagement-04 |  | Verify user is deleted when admin confirms deletion | valid |  | Confirmation prompt displayed | Click Confirm |  | User is removed from system |  |  | Draft |  | UM-04,UM-06,UM-08 | Functional | Abdelrahman khaled
TC-UserManagement-05 |  | Verify user is not deleted when admin cancels deletion | valid |  | Confirmation prompt displayed | Click Cancel |  | User remains in system |  |  | Draft |  | UM-07 | Functional | Abdelrahman khaled
Draft
TC-BookingHistory-01 |  | Verify admin can view all booked flights | valid |  | Admin logged in | Open Booking History page |  | All user bookings displayed |  |  | Draft |  | BH-01,BH-02 | Functional | Abdelrahman khaled
TC-BookingHistory-02 |  | Verify pagination allows browsing through bookings | valid |  | Multiple bookings exist | Navigate next/previous pages |  | Booking list updates per page |  |  | Draft |  | BH-03 | Functional | Abdelrahman khaled
TC-BookingHistory-03 |  | Verify confirmation prompt appears when canceling booking | valid |  | Admin on Booking History page | Click cancel booking |  | Confirmation popup displayed |  |  | Draft |  | BH-05 | Functional | Abdelrahman khaled
TC-BookingHistory-04 |  | Verify booking is canceled when admin confirms action | valid |  | Confirmation popup shown | Click Confirm |  | Booking is removed/canceled |  |  | Draft |  | BH-04,BH-06,BH-08 | Functional | Abdelrahman khaled
TC-BookingHistory-05 |  | Verify booking remains unchanged when admin cancels action | valid |  | Confirmation popup shown | Click Cancel |  | Booking remains unchanged |  |  | Draft |  | BH-07 | Functional | Abdelrahman khaled
Draft
TC-FlightSearch-01 |  | Valid that Flight Search results appears after entering valid search info. | valid |  |  |  |  | system should redirect the users to the personal details and the payment page if the “Select Journey” button has been pressed |  |  | Draft |  | FSR-01 | Functional | Al-Hussein
TC-FlightSearch-02 |  | Valid that Flight Search results appears after entering invalid search info. | Invalid |  |  |  |  | System should give no results |  |  | Draft |  | FSR-01 | Functional | Al-Hussein
Draft
TC_Login_001 |  | Verify login feature in case of user entering valid email and password | valid |  | 1-User should be already registered 2-User is already on login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | User shoould gain access and should be redirected to homepage |  |  | Draft |  | UL-06 | Functional | Ahmed Zahran
TC_Login_002 |  | Verify login feature in case of admin entering valid email and password | valid |  | Admin should be already on login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | Admin should gain access and should be redirected to User management page |  |  | Draft |  | UL-05 | Functional
TC_Login_003 |  | Verify login feature in case of user clicking on Create account button | valid |  | User is already on login page | 1-Navigate to Create account link 2-Click on the Create account link |  | User should be redirected to sign up page to register as a new user |  |  | Draft |  | UL-04 | Functional | Ahmed Zahran
TC_Login_004 |  | Verify login feature in case of user clicking on Login button when email field is empty | Invalid |  | User is already on login page | 1-Enter password in password field 2-Click on Login button |  | User should be prevented from log in and error message appears under email field "This field is required" |  |  | Draft |  | UL-01 | Functional | Ahmed Zahran
TC_Login_005 |  | Verify login feature in case of user clicking on Login button when password field is empty | Invalid |  | User is already on login page | 1-Enter email address in email field 2-Click on Login button |  | User should be prevented from log in and error message appears under password field "This field is required" |  |  | Draft |  | UL-01 | Functional | Ahmed Zahran
TC_Login_006 |  | Verify login feature in case of user logging in using invalid email format which is missing '@' | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_007 |  | Verify login feature in case of user logging in using invalid email format which is missing username | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_008 |  | Verify login feature in case of user logging in using invalid email format which is missing domain | Invalid |  | User is already on Login page | Enter email address with invalid format in email field |  | Error message should appear under email field "invalid email format" |  |  | Draft |  | UL-02 | Functional | Ahmed Zahran
TC_Login_009 |  | Verify login feature in case of user logging with invalid credentials | Invalid |  | User is already on Login page | 1-Enter email address in email field 2-Enter password in password field 3-Click on Login button |  | Error message should appear above login button "Invalid email or password" |  |  | Draft |  | UL-03 | Functional | Ahmed Zahran
Draft
TC-MyBookings_01 |  | Verify my bookings feature in case of user clicking on Book Again button | valid |  | User is already on My Bookings page | 1-Navigate to any previous booking in past bookings section 2-Click on Book Again button |  | User should be redirected to Find Flights page and Destination field should be prefilled with selected destination |  |  | Draft |  | MB-01 | Functional | Ahmed Zahran
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft
Draft

## Bug Reports
Defect_ID | Defect Title/Issue | Pre-condition | Test Data | (Test-Steps)procedures | Expected Result | Actual Result | Attachment | Priority | Probability | Severity | Bug Type | Categorization | Test case ID | Defect Status | Req ID | Created by

## RTM
Feature | SIQ | SRS | TC
Login | SIQ-2 | UL-01 | TC_Login_004 TC_Login_005
| SIQ-5 | UL-02 | TC_Login_006 TC_Login_007 TC_Login_008
| SIQ-4 | UL-03 | TC_Login_009
| SIQ-6 | UL-04 | TC_Login_003
| SIQ-7 SIQ-8 | UL-05 | TC_Login_002
| SIQ-3 | UL-06 | TC_Login_001
Register | SIQ-11 | UR-01 | TC_Registration_026 TC_Registration_027 TC_Registration_028 TC_Registration_029 TC_Registration_030
| SIQ-12 | UR-02 | TC_Registration_003 TC_Registration_004 TC_Registration_005 TC_Registration_006 TC_Registration_007 TC_Registration_008 TC_Registration_009 TC_Registration_010 TC_Registration_011
| SIQ-15 | UR-03 | TC_Registration_012
| SIQ-14 | UR-04 | TC_Registration_013 TC_Registration_014 TC_Registration_015 TC_Registration_016
| SIQ-16 | UR-05 | TC_Registration_017
| SIQ-17 | UR-06 | TC_Registration_018 TC_Registration_019 TC_Registration_020
| SIQ-18 | UR-07 | TC_Registration_021 TC_Registration_022 TC_Registration_023 TC_Registration_024
| SIQ-20 | UR-08 | TC_Registration_025
| SIQ-19 | UR-09 | TC_Registration_001
| SIQ-21 | UR-10 | TC_Registration_002
Home Page | SIQ-20 | HP-01 | TC_HomePage_01
| SIQ-20 | HP-02 | TC_HomePage_02
| SIQ-20 | HP-03 | TC_HomePage_03
| SIQ-21 | HP-04 | TC_HomePage_04
| SIQ-20 | HP-05 | TC_HomePage_05
| SIQ-20 | HP-06 | TC_HomePage_06
| SIQ-20 | HP-07 | TC_HomePage_07
| SIQ-20 | HP-08 | TC_HomePage_08
Destination Details | SIQ-23 | DD-01 | TC_DestinationDetails_01
Flight Search | REQ_5 | FS-01 | TC_FlightSearch_001, TC_FlightSearch_002, TC_FlightSearch_003
|  | FS-02 | TC_FlightSearch_001, TC_FlightSearch_004, TC_FlightSearch_005
|  | FS-03 | TC_FlightSearch_006
|  | FS-04 | TC_FlightSearch_007
|  | FS-05 | TC_FlightSearch_008
|  | FS-06 | TC_FlightSearch_009
|  | FS-07 | TC_FlightSearch_001, TC_FlightSearch_010
|  | FS-08 | TC_FlightSearch_011, TC_FlightSearch_013
|  | FS-09 | TC_FlightSearch_012, TC_FlightSearch_013
|  | FS-10 | TC_FlightSearch_001, TC_FlightSearch_014, TC_FlightSearch_015
|  | FS-11 | TC_FlightSearch_016, TC_FlightSearch_017, TC_FlightSearch_018
|  | FS-12 | TC_FlightSearch_019, TC_FlightSearch_020
|  | FS-13 | TC_FlightSearch_021, TC_FlightSearch_022, TC_FlightSearch_023, TC_FlightSearch_024
|  | FS-14 | TC_FlightSearch_025, TC_FlightSearch_026, TC_FlightSearch_027
|  | FS-15 | TC_FlightSearch_028
|  | FS-16 | TC_FlightSearch_029
|  | FS-17 | TC_FlightSearch_030, TC_FlightSearch_031
Feature | SIQ | SRS | TC
Flight Search | SIQ-30 | FRS-01 | TC-FlightSearch-01
|  | FRS-01 | TC-FlightSearch-02
Feature | SIQ | SRS | TC
Passenger Details | SIQ-32 | PD-01 | TC-PassangerDetails-01
| SIQ-33 | PD-02 | TC-PassangerDetails-02
|  | PD-03 | TC-PassangerDetails-03
|  | PD-04 | TC-PassangerDetails-04
| SIQ-34 | PD-05 | TC-PassangerDetails-02, TC-PassangerDetails-03, TC-PassangerDetails-04
| SIQ-32 | PD-06 | TC-PassangerDetails-01
| SIQ-35 | PD-07 | TC-PassangerDetails-05, TC-PassangerDetails-06
|  | PD-08 | TC-PassangerDetails-05, TC-PassangerDetails-06
| SIQ-36 | PD-09 | TC-PassangerDetails-07, TC-PassangerDetails-08
| SIQ-37 | PD-10 | TC-PassangerDetails-09
| SIQ-38 | PD-11 | TC-PassangerDetails-10
| SIQ-39 | PD-12 | TC-PassangerDetails-11
Feature | SIQ | SRS | TC
Payment | SIQ-40 | PAY-01 | TC-Payment-01
| SIQ-41 | PAY-02 | TC-Payment-02
|  | PAY-03 | TC-Payment-03
|  | PAY-04 | TC-Payment-04
|  | PAY-05 | TC-Payment-05
|  | PAY-06 | TC-Payment-06
| SIQ-42 | PAY-07 | TC-Payment-02, TC-Payment-03, TC-Payment-04, TC-Payment-05
|  | PAY-08 | TC-Payment-07
| SIQ-43 | PAY-09 | TC-Payment-08
| SIQ-44 | PAY-10 | TC-Payment-09
Feature | SIQ | SRS | TC
MY Bookings | SIQ-46 | MB-01 | TC-MyBookings-01
Feature | SIQ | SRS | TC
User Management | SIQ-48 | UM-01 | TC-UserManagement-01
|  | UM-02 | TC-UserManagement-01
| SIQ-49 | UM-03 | TC-UserManagement-02
| SIQ-50 | UM-04 | TC-UserManagement-04
| SIQ-51 | UM-05 | TC-UserManagement-03
| SIQ-51 | UM-06 | TC-UserManagement-04
| SIQ-51 | UM-07 | TC-UserManagement-05
| SIQ-49 | UM-08 | TC-UserManagement-04
Feature | SIQ | SRS | TC
Booking History | SIQ-52 | BH-01 | TC-BookingHistory-01
|  | BH-02 | TC-BookingHistory-01
| SIQ-53 | BH-03 | TC-BookingHistory-02
| SIQ-54 | BH-04 | TC-BookingHistory-04
| SIQ-55 | BH-05 | TC-BookingHistory-03
| SIQ-56 | BH-06 | TC-BookingHistory-04
| SIQ-54 | BH-07 | TC-BookingHistory-05
| SIQ-57 | BH-08 | TC-BookingHistory-04
Feature | SIQ | SRS | TC