## Risk_Register_V1
Risk_ID | Risk description | Impact description | Impact Level (1-5) | Probability Level (1-5) | Priority Level (Impact * probability) | Mitigation Notes | Status | Notes | Date Identified
Risk_01 | Lack of experience | Not all team have computer engineering background which might reduce output efficiency and quality | 5 | 5 | 25 | Prioritize crash courses and training sessions for the team | Open |  | 2026-03-30
Risk_02 | Burnout and time management risk | Team is commited to projects,exams and other courses | 4 | 4 | 16 | Distribute tasks among teams based on previous technical backgrounds to increase productivity and conduct daily meetings to monitor progress | Open |  | 2026-03-30
Risk_03 | Communication issues | Team memebers might face internet connection issues as most of the work and meetings will be done online | 3 | 1 | 3 | Team can utilize coworking spaces for internet connection or ensure all team members have stable internet connection | Open |  | 2026-03-30
Risk_04 | Tools knowledge risks | Not all team members have used tools important for the project such as jira,github and other technical tools | 4 | 3 | 12 | Sharing knowledge among team members and take courses if necessary | Open |  | 2026-03-30
Risk_05 | Tools licence risks | Some important tools might need licence to use which might delay work quality | 2 | 2 | 4 | Use alternative high quality free tools available | Open |  | 2026-03-30
Risk_06 | Members availability | Team memebers might not be available due to sickness or personal issues | 5 | 3 | 15 | Team members should know each other's task progress and ensure work transparency and have alternative plans to compensate for other members being unavailable | Open |  | 2026-03-30
Risk_07 | Client communication risks | Client meets with team members only once a week which affects constant feedback and consultation | 4 | 5 | 20 | Before each sprint, team members should have all questions ready and after the sprint all questions should be answered | Open |  | 2026-03-30
Risk_08 | Client change requests | Client might ask for a change request which might disturb work flow | 5 | 4 | 20 | Team should analyze and priortitize change requests based on importance and should have agreement and rules for change requests | Open |  | 2026-03-30
Risk_09 | Technical debt risks | taking the easy way during SDLC might cause increase in rework cost | 5 | 5 | 25 | Conduct rigorous peer reviews and ensure each step is done efficiently before moving to the next step | Open |  | 2026-03-30
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Date Identified = IF([Risk_ID]<>"", IF([Date Identified]="", TODAY(), [Date Identified]), "")