## Release#3
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Hours | Done
1 | 24 | 24 | 70 |  |  |  | sprintPlan | 100% | nabil | 3 | 3
2 | 28 | 28 |  |  |  |  | Testcase_ Flight Results | 100% | alaaa | 3 | 3
3 | 38 | 28 |  |  |  |  | Testcase_ Passenger Details | 100% | zahraan | 3 | 3
4 | 46 | 38 |  |  |  |  | Testcase_ Admin Login | 100% | alhussin | 3 | 3 |  |  | Comments | Sum of Hours | Sum of Done
5 | 58 | 46 |  |  |  |  | FlowChart A | 100% | Boda | 3 | 3 |  |  | abdalrahman | 9 | 5
6 | 70 | 70 |  |  |  |  | FlowChart B | 100% | abdalrahman | 3 | 3 |  |  | alaaa | 9 | 5
[7 empty] | SRS Review | 100% | nabil | 3 | 3 |  |  | alhussin | 11 | 7
[7 empty] | testcase review | 100% | nabil | 3 | 3 |  |  | Boda | 3 | 3
[7 empty] | learning _sequence diagram A | 100% | alhussin | 2 | 2 |  |  | nabil | 27 | 19
[7 empty] | learning _sequence diagram B | 100% | zahraan | 2 | 2 |  |  | zahraan | 11 | 7
Risks | [6 empty] | Update wireframe | 100% | nabil | 10 | 10 |  |  | Grand Total | 70 | 46
ID | Topic | Probability | Impact | Description | Handling | Actions | update Siq 1 | 100% | zahraan | 1 | 1
[7 empty] | update Siq 2 | 100% | alhussin | 1 | 1
[7 empty] | update Siq 3 | 100% | alaaa | 1 | 1
[7 empty] | update Siq 4 | 100% | abdalrahman | 1 | 1
[7 empty] | review Siq 1 | 100% | zahraan | 1 | 1
[7 empty] | review Siq 2 | 100% | alhussin | 1 | 1
[7 empty] | review Siq 3 | 100% | alaaa | 1 | 1
[7 empty] | review Siq 4 | 100% | abdalrahman | 1 | 1
[7 empty] | SRS 1 | 100% | alhussin | 2 | 2
[7 empty] | SRS 2 | 100% | abdalrahman | 2 | 2
[7 empty] | SRS 3 | 100% | zahraan | 2 | 2
[7 empty] | SRS 4 | 100% | alaaa | 2 | 2
[7 empty] | SRS v2 review | 100% | nabil | 4 | 4
[7 empty] | Testcase 1 | 100% | alhussin | 2 | 2
[7 empty] | Testcase 2 | 100% | abdalrahman | 2 | 2
Issues | [6 empty] | Testcase 3 | 100% | alaaa | 2 | 2
ID | Initiator | Probability | Impact | Description | Handling | Actions | Testcase 4 | 100% | zahraan | 2 | 2
1 |  | 5 | 5 | Stablization itiration due to lingring issues on main documents of previos releases | Mitigate | reviewing and update all work products from previous itirations | Testcase v2 review | 100% | nabil | 4 | 4
[9 empty] | Sum | 70 | 70
[12 empty] | Day | Planned | Iteam | Comment | Total
[12 empty] | 1 | 3 | sprintPlan | nabil | 24
[13 empty] | 3 | Testcase_ Flight Results | alaaa
[13 empty] | 3 | Testcase_ Passenger Details | zahraan
[13 empty] | 3 | Testcase_ Admin Login | alhussin
[13 empty] | 3 | SRS Review | nabil
[13 empty] | 3 | testcase review | nabil
[13 empty] | 3 | FlowChart A | Boda
[13 empty] | 3 | FlowChart B | abdalrahman
[12 empty] | 2 | 2 | learning _sequence diagram A | alhussin | 4
[13 empty] | 2 | learning _sequence diagram B | zahraan
[12 empty] | 3 | 10 | Update wireframe | nabil | 10
[12 empty] | 4 | 1 | update Siq 1 | zahraan | 8
[13 empty] | 1 | update Siq 2 | alhussin
[13 empty] | 1 | update Siq 3 | alaaa
[13 empty] | 1 | update Siq 4 | abdalrahman
[13 empty] | 1 | review Siq 1 | zahraan
[13 empty] | 1 | review Siq 2 | alhussin
[13 empty] | 1 | review Siq 3 | alaaa
[13 empty] | 1 | review Siq 4 | abdalrahman
[12 empty] | 5 | 2 | SRS 1 | alhussin | 12
[13 empty] | 2 | SRS 2 | abdalrahman
[13 empty] | 2 | SRS 3 | zahraan
[13 empty] | 2 | SRS 4 | alaaa
[13 empty] | 4 | SRS v2 review | nabil
[12 empty] | 6 | 2 | Testcase 1 | alhussin | 12
[13 empty] | 2 | Testcase 2 | abdalrahman
[13 empty] | 2 | Testcase 3 | alaaa
[13 empty] | 2 | Testcase 4 | zahraan
[13 empty] | 4 | Testcase v2 review | nabil
[15 empty] | Sum | 70